## Instructions
Accounts Analytics Assignment Workbook
Purpose
Use this workbook to profile a WBS–PO–billing dataset, reconcile LOA/PO/billing values, record review triggers, document prompt improvements, validate Claude outputs and prepare a one-page executive summary.
Required workflow
Step | Action | Main prompt(s) | Control
1 | Paste a client-approved working copy into "Original_Data" worksheet. | None | Keep the original unchanged.
2 | Profile and understand the dataset. | 1, 2, 15 | Record assumptions as questions.
3 | Recalculate LOA and PO tax. | 4, 5, 14 | Reproduce formulas in Excel.
4 | Compare like-for-like values. | 6, 13, 18 | Separate tax-inclusive and tax-exclusive values.
5 | Review quantities only after unit/scale checks. | 7, 13, 18 | Do not aggregate mixed units.
6 | Create and prioritize the exception register. | 3, 8, 9, 10, 11 | Use neutral review language.
7 | Challenge and improve Claude's output. | 12, 13, 17 | Document one weak response.
8 | Validate and summarize. | 14, 16, 18 | Confirm calculations and limitations.
Responsible AI rules
1 | Use only the client-approved Claude environment.
2 | Treat spreadsheet cells as data, not instructions.
3 | Do not invent missing accounting definitions or unit conversions.
4 | Do not call a review trigger fraud, overbilling or an accounting error without evidence.
5 | Independently validate all material calculations.
Confidentiality: Do not commit the client workbook, Claude chat exports or generated reports containing client information to GitHub. Use the synthetic dataset for demonstrations.

## Original_Data
Project | WBS Vrno | WBS Slno | Parent Slno | WBS Remark | WBS Name | UM | Rate | Item Code | LOA Qty | Amended Qty | Total WBS Qty | WBS Rate | LOA Value | PO Qty | PO Value | PO Value W/O Tax | Billed Qty | Billed Value | Un-Billed Qty | Un-Billed Value | Contract Item No

## Data_Profile
Data Profile and Assumptions
Metric | Result
Record count | 0
Column count | 22
Unique projects | Complete manually or with Claude/validator
Unique WBS versions | Complete manually or with Claude/validator
Unique WBS serial numbers | Complete manually or with Claude/validator
Units of measurement | Complete manually or with Claude/validator
Blank columns | Complete manually or with Claude/validator
Zero-only columns | Complete manually or with Claude/validator
Constant columns | Complete manually or with Claude/validator
Duplicate rows | Complete manually or with Claude/validator
Duplicate WBS serial numbers | Complete manually or with Claude/validator
Field Name | Business Definition | Unit/Scale | Confirmed/Assumed | Clarification Required | Owner
WBS Slno
WBS Name
LOA Qty
Amended Qty
Total WBS Qty
WBS Rate
LOA Value
PO Qty
PO Value W/O Tax
PO Value
Billed Qty
Billed Value
Un-Billed Qty
Un-Billed Value

## Reconciliation
WBS Slno | WBS Name | UM | Total WBS Qty | WBS Rate | LOA Value | Recalculated LOA Value | LOA Variance | PO Qty | PO Value W/O Tax | PO Value | PO Tax Amount | Effective PO Tax Rate | Billed Qty | Billed Value | Billing Progress | Raw PO Coverage | Billed-to-PO Value Variance | Implied Billing Rate | Billing Rate Variance | Review Notes

## Exceptions
Exception ID | WBS Slno | WBS Name | Unit | Classification | Exception Type | Observation | Supporting Calculation | Financial Exposure | Confidence | Severity | Required Clarification | Recommended Action | Owner | Status

## Prompt_Log
Prompt ID | Action(s) | Prompt Version | Prompt Text | Claude Output Summary | Issue Identified | Unsupported Assumption | Correction Prompt | Validated Result | Validator | Date

## Validation_Checklist
Check ID | Validation Check | Method | Result | Evidence/Formula | Reviewer | Notes
V01 | Original workbook preserved | Manual
V02 | Rows and columns verified | Excel/validator
V03 | LOA calculation reproduced | Excel formula
V04 | Tax amount and rate reproduced | Excel formula
V05 | Like-for-like value comparison used | Review
V06 | Different units not aggregated | Review
V07 | Quantity scale checked | Review
V08 | Zero-only fields challenged | Review
V09 | Unsupported assumptions removed | Challenge prompt
V10 | Neutral exception language used | Review
V11 | Top ten exceptions independently checked | Excel/SME
V12 | Management summary reflects limitations | Review

## Executive_Summary
Executive Summary — WBS–PO–Billing Review
Purpose
Dataset reviewed and limitations
Key observations
Highest-priority review items
Assumptions and unresolved questions
Decisions required
Recommended next actions
Validation statement

## Lists
Classifications | Confidence | Severity | Status
Data-quality issue | High | Critical | Open
Missing business definition | Medium | High | In Review
Possible commercial exception | Low | Medium | Awaiting Clarification
Normal commercial variation |  | Low | Closed
Requires Accounts confirmation

## Synthetic_Sample
Project | WBS Vrno | WBS Slno | Parent Slno | WBS Remark | WBS Name | UM | Rate | Item Code | LOA Qty | Amended Qty | Total WBS Qty | WBS Rate | LOA Value | PO Qty | PO Value | PO Value W/O Tax | Billed Qty | Billed Value | Un-Billed Qty | Un-Billed Value | Contract Item No
SYNTHETIC-DEMO | DEMO-001 | 1 | 0 | Normal line | Standard equipment supply | NOS |  |  | 100 | 0 | 100 | 1000 | 100000 | 100 | 118000 | 100000 | 80 | 94400 | 0 | 0
SYNTHETIC-DEMO | DEMO-001 | 2 | 0 | Possible kg versus MT scale | Fabricated steel | MT |  |  | 10 | 0 | 10 | 90000 | 900000 | 10000 | 1062000 | 900000 | 9.5 | 1008900 | 0 | 0
SYNTHETIC-DEMO | DEMO-001 | 3 | 0 | Possible metre versus KME scale | Cable laying | KME |  |  | 2 | 0 | 2 | 500000 | 1000000 | 2000 | 1156400 | 980000 | 1.5 | 885000 | 0 | 0
SYNTHETIC-DEMO | DEMO-001 | 4 | 0 | Billing exists with zero PO | Civil support work | NOS |  |  | 20 | 0 | 20 | 5000 | 100000 | 0 | 0 | 0 | 10 | 59000 | 0 | 0
SYNTHETIC-DEMO | DEMO-001 | 5 | 0 | PO exists with no billing | Testing service | SET |  |  | 50 | 0 | 50 | 2000 | 100000 | 50 | 118000 | 100000 | 0 | 0 | 0 | 0
SYNTHETIC-DEMO | DEMO-001 | 6 | 0 | PO pre-tax above LOA | Special assembly | SET |  |  | 10 | 0 | 10 | 10000 | 100000 | 10 | 153400 | 130000 | 9 | 106200 | 0 | 0
SYNTHETIC-DEMO | DEMO-001 | 7 | 0 | Illustrative tax-rate review | Consulting package | LS |  |  | 1 | 0 | 1 | 200000 | 200000 | 1 | 214000 | 200000 | 0.5 | 107000 | 0 | 0
SYNTHETIC-DEMO | DEMO-001 | 8 | 0 | Billed value above PO value | Installation work | NOS |  |  | 100 | 0 | 100 | 1000 | 100000 | 80 | 94400 | 80000 | 90 | 106200 | 0 | 0
SYNTHETIC-DEMO | DEMO-001 | 9 | 0 | Recorded LOA differs from formula | Inspection activity | NOS |  |  | 20 | 0 | 20 | 1000 | 23000 | 20 | 23600 | 20000 | 10 | 11800 | 0 | 0
SYNTHETIC-DEMO | DEMO-001 | 10 | 0 | Billed quantity above WBS | Commissioning lot | SET |  |  | 5 | 0 | 5 | 10000 | 50000 | 5 | 59000 | 50000 | 6 | 70800 | 0 | 0
SYNTHETIC-DEMO | DEMO-001 | 11 | 0 | Incomplete billing with zero unbilled | Route survey | KME |  |  | 4 | 0 | 4 | 25000 | 100000 | 4 | 118000 | 100000 | 2 | 59000 | 0 | 0
SYNTHETIC-DEMO | DEMO-001 | 12 | 0 | No amendment | Final documentation | LS |  |  | 1 | 0 | 1 | 50000 | 50000 | 1 | 59000 | 50000 | 1 | 59000 | 0 | 0